# Project Report

## Freelancer Data

| Freelancer | Skill | Cost per Day | Experience (Years) |
| --- | --- | --- | --- |
| Alice | Planning | 300 | 5 |
| Bob | Data Collection | 320 | 4 |
| Cara | Data Cleaning | 350 | 3 |
| Dan | EDA | 330 | 4 |
| Ella | Modeling | 400 | 6 |

## Task Data

| Task ID | Task Name | Required Skill | Duration (days) | Dependencies |
| --- | --- | --- | --- | --- |
| T01 | Define Requirements | Planning | 2 | nan |
| T02 | Collect Data | Data Collection | 4 | T01 |
| T03 | Preprocess Data | Data Cleaning | 3 | T02 |
| T04 | EDA | EDA | 3 | T03 |
| T05 | Train Model | Modeling | 5 | T04 |
| T06 | Validate Model | Modeling | 2 | T05 |
| T07 | Document Findings | Writing | 2 | T04 |
| T08 | Create Dashboard | Visualization | 4 | T06 |
| T09 | Prepare Report | Writing | 3 | T07,T08 |
| T010 | Review & Submit | Review | 2 | T09 |

## Cost Matrix

|  | T1 | T2 | T3 | T4 | T5 | T6 | T7 | T8 | T9 | T10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| F1 | 60.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 |
| F2 | 10000.00 | 80.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 |
| F3 | 10000.00 | 10000.00 | 116.67 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 |
| F4 | 10000.00 | 10000.00 | 10000.00 | 82.50 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 10000.00 |
| F5 | 10000.00 | 10000.00 | 10000.00 | 10000.00 | 66.67 | 66.67 | 10000.00 | 10000.00 | 10000.00 | 10000.00 |

## Assignments (Hungarian Method)

| Freelancer | Skill | Experience | Task ID | Task Name | Cost/Day | Duration | Total Cost |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alice | Planning | 5 | T01 | Define Requirements | 300 | 2 | 600 |
| Bob | Data Collection | 4 | T02 | Collect Data | 320 | 4 | 1280 |
| Cara | Data Cleaning | 3 | T03 | Preprocess Data | 350 | 3 | 1050 |
| Dan | EDA | 4 | T04 | EDA | 330 | 3 | 990 |
| Ella | Modeling | 6 | T05 | Train Model | 400 | 5 | 2000 |

## CPM Task Schedule

| Task | Name | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | Define Requirements | 0 | 2 | 0 | 2 | 0 |
| T02 | Collect Data | 2 | 6 | 2 | 6 | 0 |
| T03 | Preprocess Data | 6 | 9 | 6 | 9 | 0 |
| T04 | EDA | 9 | 12 | 9 | 12 | 0 |
| T05 | Train Model | 12 | 17 | 12 | 17 | 0 |
| T06 | Validate Model | 17 | 19 | 17 | 19 | 0 |
| T07 | Document Findings | 12 | 14 | 21 | 23 | 9 |
| T08 | Create Dashboard | 19 | 23 | 19 | 23 | 0 |
| T09 | Prepare Report | 23 | 26 | 23 | 26 | 0 |
| T010 | Review & Submit | 26 | 28 | 26 | 28 | 0 |

## Critical Path Graph

## Summary

Total Assignment Cost: $5920.00

Budget Exceeded by $920.00

Critical Path: T01 → T02 → T03 → T04 → T05 → T06 → T08 → T09 → T010

Project Duration: 28 days